Cornea Clinic EMR

Production Stabilization Roadmap

Based on: Global Production Audit (June 2026)

Principle: Stabilize production before adding new clinical features

The platform scores 86/100 on clinical breadth but 78/100 on production readiness. Recent critical incidents (login recursion, Keratoplasty script load failure) demonstrate that reliability gaps can disable entire modules silently.

# Three-layer approach

| Layer | Focus | Target window |
| --- | --- | --- |
| 1 — Safety | PHI protection, backups, auth, media durability | Weeks 0–4 |
| 2 — Reliability | Sync integrity, regression tests, monitoring, runbooks | Weeks 4–12 |
| 3 — Scalability | Object storage, rate limits, performance, multi-user load | Months 3–6 |

Clinical feature freeze: No new modules (appointments, DICOM, FHIR, new registries, AI v2) until Phase 3 exit gates are met. Bug fixes and security patches remain in scope at all times.

# Stabilization gates (G1–G7)

Production is stabilized when all gates pass:

| Gate | Criterion | Verification |
| --- | --- | --- |
| G1 — Data safety | DB + media backed up; restore drill within 30 days | backup-restore-drill.ps1 log |
| G2 — Media durability | MEDIA_STORAGE_PROVIDER=s3 on production | Upload + retrieve test |
| G3 — Auth hardening | AUTH_EXPOSE_REFRESH_IN_BODY=false, explicit CORS, SMTP | Password-reset email test |
| G4 — Regression safety | Playwright CI: login, KP tabs, script load, sync | CI green on main |
| G5 — Sync reliability | Unified or verified sync for all registries | Sync test matrix pass |
| G6 — Security baseline | Global rate limiting; pen-test scoped | Redis limiter active |
| G7 — Observability | Health, backup, sync failure alerts | Alert drill passed |

# Phase 0 — Immediate hardening (Days 0–14)

## 0.1 Production configuration audit

| Task | Effort |
| --- | --- |
| Confirm NODE_ENV=production on DigitalOcean API | 1 h |
| Set AUTH_EXPOSE_REFRESH_IN_BODY=false | 30 m |
| Set explicit CORS_ORIGIN (not *) | 30 m |
| Verify migrations 000–019 on production DB | 2 h |
| Document DO env vars in secure runbook | 2 h |

## 0.2 Live smoke test

- Cloud login completes; modal dismisses without refresh

- Keratoplasty: all four sub-tabs switch

- Visit save → sync push succeeds

- Record lock acquire/release

- KC registry read/write

- Media upload on test visit

## 0.3 Backup and recovery

- Schedule production DB backup (CorneaEMR-ProductionBackup)

- Run backup-restore-drill.ps1 with row-count verification

- Store backup-encryption.key off-site

- Review backup logs weekly

# Phase 1 — Safety (Weeks 2–4)

## 1.1 Object storage for clinical media (critical)

Risk: local media on ephemeral DO containers loses images on redeploy.

- Provision S3-compatible bucket (DO Spaces or Cloudflare R2)

- Set MEDIA_STORAGE_PROVIDER=s3 on production API

- Run media migration CLI to backfill existing assets

- Verify signed URL upload/download from clinic UI

- Include object storage in backup strategy

## 1.2 SMTP and account recovery

- Configure production SMTP; run test:smtp

- End-to-end password reset test

## 1.3 Security quick wins

- Tighten record-lock release to kp:write only

- Restrict public /health DB details

- Review RBAC for production users

## 1.4 Prevent script-load regressions

- CI scan for duplicate top-level declarations vs storage.js

- Fail PR on collision; document contributor rule

# Phase 2 — Reliability (Weeks 4–12)

## 2.1 Unified registry sync

KC, keratitis, graft, and eye-bank use direct REST while visits use the main sync queue — offline edits are inconsistent.

- Inventory all registry write paths

- Extend sync queue OR document explicit offline policy per registry

- Document conflict rules in SYNC_ARCHITECTURE.md

- Integration test: offline edit → reconnect → data consistent

## 2.2 Playwright regression suite

| Test | Covers |
| --- | --- |
| Script load | No SyntaxError; switchKpPanel defined |
| Login bootstrap | No recursion; modal closes |
| KP panel switch | All four sub-panels |
| Sync smoke | Push/pull on staging |
| Auth 401 | Registry routes require token |

## 2.3 Operational runbooks

- Incident response: login down, sync stuck, API 5xx

- Deployment rollback: Clinic (Wrangler) + API (DO)

- Backup restore from BACKUP_RECOVERY.md

## 2.4 Monitoring and alerts

- API /health non-200 or DB latency > 2s

- Missed backup scheduled run

- Sync queue backlog threshold

- API 5xx error spike

# Phase 3 — Scalability (Months 3–6)

## 3.1 API rate limiting

- Deploy Redis for global rate limits (replaces in-memory limiter)

- Per-IP and per-user limits on auth and sync

- Document horizontal scaling path for DO App Platform

## 3.2 Performance

- Defer non-critical scripts; measure LCP

- Server-side pagination for patient search

- Archive old visits in IndexedDB

- Lazy-load clinical library thumbnails

## 3.3 Codebase hardening

- Wrap clinic JS in IIFEs or ES modules

- Centralize store keys in storage.js only

- Staging environment mirroring production

## 3.4 Formal security assessment

- OWASP scope: auth, sync, upload, tenant isolation

- Remediate findings before feature freeze lift

# Phase 4 — Feature readiness (after G1–G7)

| Priority | Feature | Rationale |
| --- | --- | --- |
| P1 | Dashboard institute KPIs | Ops visibility; small effort |
| P2 | Offline research summaries | Reliability extension |
| P3 | Sirius / tomography import | Builds on stable media |
| P4 | FHIR export prototype | Tertiary bridge |
| P5 | Appointments & recall | Needs stable sync |
| P6 | DICOM / PACS | Depends on media + performance |
| P7 | New clinical modules | Deferred until platform proven |

# Deferred clinical backlog (freeze list)

- Appointment & recall module

- DICOM ingest

- Dry eye / OSD module

- OR scheduling

- Teaching case library

- FHIR / national registry

- LDAP/SSO

- Topography ML v2

- Mobile visit summary

# Success metrics (6-month targets)

| Metric | Baseline | Target |
| --- | --- | --- |
| Production readiness | 78 | ≥ 90 |
| Security | 72 | ≥ 85 |
| Scalability | 70 | ≥ 80 |
| Script-load outages | 2 critical in 2026 | 0 |
| Restore drill | Ad hoc | Monthly, logged |

# Quick start (this week)

- 1. Run live smoke test checklist

- 2. Execute backup-restore-drill.ps1

- 3. Audit DO env: MEDIA_STORAGE_PROVIDER and SMTP

- 4. Add CI duplicate-global scan

- 5. Schedule S3 migration window

Revisit gate status monthly. Lift the clinical feature freeze only when G1–G7 are demonstrably met.